## Sheet1
Ticket | Description | Ticket created on | Status | Remarks
KGI-444 | Same email is read multiple times creating multiple rows in the application | 18/08/2025 | UAT | -Unable to reproduce the issue in Test. - Reworked on how the code sets the mail to read status (assumption of application reading the mails might have affected at any point)
KGI-442 | Unable to save the invoice in exact creating multiple entries in the exact | 2025-08-08 | In Progress | -Unable to reproduce the issue in Test. - Assumptions that the exact function for adding rows is causing the issue but unable to reproduce it. - Tom J tried to figure it out but unable to do so , bijoy needs some more time to fix this
KGI-439 | Data linking issue between invoice and fields | 16/07/2025 | To-do | -Textract issue -The issue is happening for a particular venodrs invoice (reported a couple of times) -Unable to reproduce in the test -Added a log in the prod to capture next mapping and analyse it (according to Bijoy)